# Xamarinbot V2 - Detailed Development Roadmap

Step-by-step implementation plan for data, mathematical kernel, replay, probability modeling, execution MPC, validation, and staged live rollout

Version 2.0  |  13 August 2026

Roadmap principle. Do not implement the full stochastic MPC first. Build the system in layers so every new capability is replayable, measurable, and removable by feature flag. The exact portfolio kernel and causal event store come before predictive complexity.

Target architecture: event-driven Market State Estimator -> Probability/Regime Model -> Portfolio Controller -> Execution Optimizer -> CLOB, with a receding-horizon loop that can place, cancel, replace, or wait based on new conditions.

# Contents

1. Program Goals and Definition of Done

2. Architecture and Version Strategy

3. Phase 0 - Baseline Freeze and Audit

4. Phase 1 - Market Data and Clock Foundation

5. Phase 2 - Causal Event Store and Replay Engine

6. Phase 3 - Exact Portfolio Mathematics Kernel

7. Phase 4 - Feature Engineering: TWAP, Spot, CLOB, Time

8. Phase 5 - Probability Model and Calibration

9. Phase 6 - Seed Regime / Middle-Ground State Machine

10. Phase 7 - Order-Book and Execution Simulator

11. Phase 8 - One-Step Semi-Controlled Optimizer

12. Phase 9 - Proactive Maker/Taker Place-Cancel-Replace

13. Phase 10 - Short-Horizon MPC

14. Phase 11 - Walk-Forward Calibration and Ablations

15. Phase 12 - Shadow / Paper Trading

16. Phase 13 - Limited Live Rollout

17. Phase 14 - Adaptive Optimization and Target-Profile Research

18. Testing Matrix

19. Observability and UI

20. Data Schema and Journaling

21. Risk Gates and Rollback Plan

22. Recommended Milestones and Deliverables

23. References

# 1. Program Goals and Definition of Done

## 1.1 Goals

Retain a causal, testable version of the current Xamarinbot baseline for comparison.

Use the market-configured Chainlink TWAP as settlement-state input and current BTC as a leading timing input.

Replace fixed sign-only decisions with calibrated probability / fair-value estimation.

Make entry timing, maker/taker mode, limit price, quantity, TTL, cancel, and replace controllable decisions.

Manage exact portfolio payoff with U, D, C, Pi_U, Pi_D, G, and R.

Reduce large single-round losses and improve net expectancy after realistic execution costs.

Create an event-driven semi-controlled / receding-horizon optimizer that can be audited in replay.

## 1.2 Definition of Done

| Dimension | Done condition |
| --- | --- |
| Correctness | Same event log -> same decisions and fills in deterministic replay; exact portfolio identities reconcile to settlement. |
| Data integrity | No future data leakage; source timestamps and local receive timestamps recorded. |
| Execution realism | Depth, partial fills, fees, tick size, pending delay, cancel/replace and open-order state modeled. |
| Model quality | q calibrated out of sample; lead-lag hypotheses verified by ablation. |
| Risk | G_min and spend limits enforced before order submission and after pending fills. |
| Performance | Event-to-decision latency measured; optimizer finishes inside configured budget. |
| Profitability research | Full strategy improves out-of-sample net expectancy and tail-loss profile versus baseline. |

# 2. Architecture and Version Strategy

Use feature flags and versioned configuration so the baseline, one-step optimizer, and MPC can run side by side on identical event streams. Every phase must have an explicit exit gate before the next phase becomes production-critical.

| Version | Theme | Outcome |
| --- | --- | --- |
| V1.0 | Frozen baseline | Current three-signal + existing execution/replay behavior, instrumented. |
| V1.1 | Data/replay foundation | Causal event store, deterministic portfolio ledger, exact platform metadata. |
| V1.2 | Portfolio controller | G/R payoff kernel and risk-constrained sizing. |
| V1.3 | Lead-lag model | TWAP + current BTC + time/volatility features. |
| V1.4 | Probability engine | Calibrated q and fair value. |
| V1.5 | State machine | Middle-ground candidate action matrix. |
| V1.6 | Execution simulator | Depth/fees/fills/delay/maker queue. |
| V2.0 | One-step controller | Joint price/qty/timing candidate optimization. |
| V2.1 | Proactive order lifecycle | Condition-driven place/cancel/replace. |
| V2.2 | Short-horizon MPC | Receding-horizon sequence optimization. |
| V2.3 | Shadow + live gates | Staged deployment. |
| V2.4+ | Adaptive calibration | Ongoing statistical optimization, not uncontrolled online learning. |

# 3. Phase 0 - Baseline Freeze and Audit

Objective. Create a trustworthy reference implementation and measurement baseline before changing strategy behavior.

## Implementation steps

Tag/freeze the current strategy configuration and code path used for live/paper/replay.

Record all existing parameters: decision window, lookbacks, minimum gap, clip, ask range, fee fallback, freshness, limit delta, retries, residual/spend caps.

Add a strategy_version and config_hash to every journaled decision/fill/settlement.

Run a baseline replay set and export win rate, average win/loss, profit factor, largest single loss, max drawdown, fees, fill rate, and PnL by entry price/time.

Create a baseline failure taxonomy: high-price loss, late entry, false TWAP confirmation, reversal, stale data, missed/partial fill, oversizing.

## Deliverables

Baseline code tag and immutable config snapshot.

Baseline performance report.

Decision/fill journal schema v1.

Regression dataset of representative rounds.

## Verification

Replay the same dataset twice and compare identical decisions.

Reconcile settlement PnL to account journal.

Verify all baseline skip reasons are observable.

## Exit gate

Baseline results are reproducible.

No V2 work modifies the baseline path without a feature flag.

# 4. Phase 1 - Market Data and Clock Foundation

Objective. Build low-latency, timestamp-correct inputs for official TWAP, current BTC, CLOB, order/user events, and runtime market configuration.

## Implementation steps

Implement market discovery and round clock with explicit start_ts, end_ts, t and tau.

Fetch token IDs, current tick size, minimum order size, fee parameters, and delay flags at market start; subscribe to tick-size changes.

Implement official Chainlink TWAP RTDS client using observation timestamp, reconnect/resubscribe logic, and configurable 30/60 second window mapping.

Implement current BTC leading-price feed. Prefer a low-latency robust source/composite; record provider timestamp and receive timestamp.

Implement CLOB market-channel book deltas plus periodic/safety resnapshot; record book hash where available.

Implement authenticated user/order stream for open orders, partial fills, matched/confirmed transitions, and reconciliation.

Synchronize host clocks and continuously record clock offset/latency metrics.

## Deliverables

MarketConfig runtime object.

TWAP/spot/book/user adapters.

Feed freshness monitor.

Clock/latency dashboard.

## Verification

Disconnect/reconnect tests.

Stale timestamp rejection.

Tick-size-change test.

Out-of-order event test.

Cross-feed clock skew test.

## Exit gate

All feeds survive reconnect without silent state corruption.

Every event has source and receive timestamps.

Market configuration is no longer hardcoded.

## Main risks / controls

Never infer TWAP window from update cadence.

Do not submit orders when state freshness is uncertain.

# 5. Phase 2 - Causal Event Store and Replay Engine

Objective. Make every future strategy experiment replayable with no look-ahead and with realistic order lifecycle.

## Implementation steps

Define append-only event types: MARKET_CONFIG, TWAP, SPOT, BOOK_SNAPSHOT, BOOK_DELTA, ORDER_SUBMIT, ORDER_STATUS, FILL, CANCEL, SETTLEMENT.

Persist nanosecond/millisecond timestamps as received and source timestamps separately.

Create deterministic event ordering rules for ties.

Build replay clock that exposes only events with event_time <= decision_time.

Support event-driven decisions plus a configurable heartbeat.

Add reproducible random seeds for stochastic fill models used only when historical queue data is insufficient.

## Deliverables

Event store schema v2.

ReplayRunner v2.

Causality audit report.

## Verification

Inject future events and confirm they are inaccessible.

Replay round with disconnect/resnapshot.

Replay partial fill + cancel remainder.

## Exit gate

Causality tests pass.

Replayed portfolio ledger matches recorded fills exactly when fills are known.

# 6. Phase 3 - Exact Portfolio Mathematics Kernel

Objective. Implement the exact U/D/C payoff controller independently of prediction logic.

## Implementation steps

Create PortfolioState with U, D, C, Pi_U, Pi_D, G, R.

Update C from actual fill price, size and actual taker fee; maker fee is zero under current rules but read fee configuration.

Implement simulateFill(action) without mutating live state.

Implement alpha-order EV and hedge-order risk contribution separately.

Implement G_min, P_min, spend and position constraints.

Implement derived maximum directional spend and hedge quantity formulas.

Add property-based tests over random fill sequences.

## Deliverables

portfolio_math module.

Candidate-action simulator.

Portfolio unit/property test suite.

## Verification

Identity: Pi_U == U-C.

Identity: Pi_D == D-C.

Identity: G == min(Pi_U,Pi_D).

Identity: R == Pi_U-Pi_D.

Random multi-fill reconciliation.

## Exit gate

100% mathematical kernel test pass.

Kernel has no dependency on predictor or exchange client.

# 7. Phase 4 - Feature Engineering: TWAP, Spot, CLOB, Time

Objective. Construct the causal state vector required to compare TWAP-only, spot-only, and lead-lag models.

## Implementation steps

Compute raw TWAP gap G_T and current-BTC gap G_S.

Compute spot-to-TWAP lead gap L.

Compute fixed-horizon spot returns at multiple horizons.

Compute robust CLOB log-odds returns and midpoint direction.

Compute order-flow/depth imbalance and spread.

Compute realized volatility and Z_gap normalized by remaining time.

Compute modeled TWAP-pressure feature without attempting to reproduce the official Chainlink TWAP.

Store all features with feature_version.

## Deliverables

FeatureEngine v1.

Feature research parquet/DB tables.

Lead-lag analysis notebook/report.

## Verification

No feature may consume a future timestamp.

Feature output invariant between live and replay.

Missing/stale inputs produce explicit invalid state.

## Exit gate

Feature set is deterministic and causal.

TWAP-only vs spot-only vs combined datasets are ready for modeling.

# 8. Phase 5 - Probability Model and Calibration

Objective. Estimate fair probability q rather than trading on sign agreement alone.

## Implementation steps

Build a logistic-regression baseline using Z_gap, lead gap, spot momentum, CLOB momentum, OFI, volatility, tau and selected interactions.

Create walk-forward train/validation/test splits by time, never random row splits across adjacent observations.

Calibrate probability with isotonic or Platt-style calibration only on validation data if needed.

Report q calibration by time bucket, gap bucket, price bucket and volatility regime.

Compare TWAP-only, current-BTC-only and combined lead-lag models.

Freeze model artifact, feature version, training window and metrics into ModelRegistry.

## Deliverables

q_model v1.

Calibration report.

Model registry metadata.

## Verification

Brier/log-loss.

Calibration plots.

Out-of-sample settlement accuracy.

Economic edge conditional on q-price.

## Exit gate

Combined model must beat or justify complexity relative to simpler baselines.

No production use until calibration is acceptable.

# 9. Phase 6 - Seed Regime / Middle-Ground State Machine

Objective. Encode the hand-drawn middle-ground logic as candidate-action permissions while preserving optimizer override.

## Implementation steps

Represent raw/normalized gap states and CLOB/spot directions as explicit enums.

Encode corrected seed rules: bullish synchronized -> TAKER UP candidate; bullish structural + CLOB pullback -> MAKER UP; bearish mirror states -> DOWN candidates.

Encode WAIT/CANCEL for conflict, flat, stale or invalid states.

Keep the original baseline rule available as a separate policy.

Log regime transitions and dwell times.

## Deliverables

RegimeClassifier.

ActionPermissionMatrix.

Transition statistics report.

## Verification

Unit test every matrix cell.

Replay transitions around ±1/±0.5/0 seeds.

Verify no matrix entry directly bypasses EV/risk gates.

## Exit gate

All seed states are deterministic and auditable.

# 10. Phase 7 - Order-Book and Execution Simulator

Objective. Model the difference between theoretical fair value and executable PnL.

## Implementation steps

Build taker cost curve by walking current ask depth for requested size.

Apply current fee parameters to simulated taker fills.

Model 250 ms taker delay on markets where enabled, including revalidation/repricing risk.

Implement FAK partial fill semantics.

Implement maker queue/fill model using distance to touch, queue depth, trade flow, state and time.

Estimate q_fill / maker adverse selection from historical fills.

Implement cancel and replace with order-state reconciliation.

## Deliverables

ExecutionSimulator v1.

Maker fill model v1.

Taker slippage/delay report.

## Verification

Historical fill replay where data available.

Depth walking tests.

Partial FAK tests.

Pending-delay no-cancel test.

## Exit gate

Execution model error is quantified and within research tolerance before PnL claims.

# 11. Phase 8 - One-Step Semi-Controlled Optimizer

Objective. Jointly choose side, execution mode, price and quantity for the current state without yet optimizing a multi-step future sequence.

## Implementation steps

Generate discrete candidate actions from the regime classifier.

Generate taker quantities from depth levels and portfolio risk budget.

Generate maker prices on the valid current tick grid and candidate quantities.

For each action, simulate EV_after, G_after, Pi_U/Pi_D, cost and operational penalties.

Reject hard-constraint violations.

Select the highest-value action; include WAIT as a candidate with value 0 / continuation estimate.

Record the complete candidate table for each decision.

## Deliverables

OneStepController v1.

Candidate diagnostics UI/table.

## Verification

Compare against baseline on identical replay.

Verify optimizer never violates G_min.

Stress test many book/portfolio states.

## Exit gate

One-step controller improves economic metrics or reveals exactly why it does not.

# 12. Phase 9 - Proactive Maker/Taker Place-Cancel-Replace

Objective. Make order lifetime condition-driven rather than fixed.

## Implementation steps

Attach origin_state_id, purpose, q_at_submit, fair_value, G_after_if_fill, expiry policy and cancel predicates to every order.

Recompute open-order value on every relevant event.

Cancel when edge fails, regime flips, risk changes, data becomes stale, or time compression makes passive execution irrational.

Replace only when the new expected value exceeds the old order by a churn threshold.

Rate-limit cancel/replace to protect latency, API limits and queue priority.

Measure cancel regret: canceled orders that would have filled profitably versus kept orders that became adversely selected.

## Deliverables

OrderSupervisor v1.

Cancel/replace analytics.

## Verification

Rapid regime flip.

Partial fill then cancel.

Tick-size change with open order.

Feed stale while maker order rests.

## Exit gate

Open orders always have a currently valid thesis or are canceled.

# 13. Phase 10 - Short-Horizon MPC

Objective. Add timing value by comparing act-now, wait, maker, taker and repair sequences over a short horizon.

## Implementation steps

Define small discrete scenario tree for spot/TWAP/CLOB/book evolution over 0.25-5 seconds.

Estimate transition probabilities from historical state transitions.

Optimize a short action sequence but execute only the first action.

Include continuation value for WAIT and resting maker states.

Bound computation time; fall back to one-step controller if deadline exceeded.

Start with a horizon of 1-3 decision steps before expanding.

## Deliverables

MPCController v1.

Scenario/transition model.

Controller latency benchmark.

## Verification

MPC action equals one-step action in degenerate horizon.

Timeout fallback.

Scenario probability sanity checks.

## Exit gate

MPC produces measurable timing improvement after churn/latency costs.

# 14. Phase 11 - Walk-Forward Calibration and Ablations

Objective. Determine which components create real out-of-sample value.

## Implementation steps

Run rolling train/validate/test windows across many rounds and volatility regimes.

Run mandatory ablations: TWAP-only, spot-only, combined, no CLOB, no maker, no portfolio repair, no MPC.

Optimize only on training/validation; lock parameters before each test segment.

Analyze results by time bucket, gap bucket, BESTASK, volatility, liquidity and action type.

Track parameter stability and sensitivity, not only best parameter values.

## Deliverables

Walk-forward report.

Ablation matrix.

Parameter sensitivity report.

## Verification

No test-period tuning.

Bootstrap confidence intervals on PnL/EV metrics.

## Exit gate

Full model has a defensible incremental benefit over simpler alternatives.

# 15. Phase 12 - Shadow / Paper Trading

Objective. Validate real-time data, timing and order decisions without capital risk.

## Implementation steps

Run production feeds and controller continuously while submitting no real orders.

Record desired order, hypothetical submit time, expected fill and real subsequent book evolution.

Run a parallel paper executor with realistic delay/queue assumptions.

Compare live shadow decisions with offline replay for the same timestamps.

Measure event latency percentiles and missed-decision rate.

## Deliverables

Shadow service.

Daily shadow report.

Live-vs-replay parity report.

## Verification

24/7 reconnect stability.

No timestamp leakage.

Controller deadlines met.

## Exit gate

At least a meaningful sample of rounds with stable live/replay parity before live capital.

# 16. Phase 13 - Limited Live Rollout

Objective. Deploy with minimal capital and hard downside controls, then expand only after reconciliation.

## Implementation steps

Start with one market at a time and small max spend / G_min.

Enable one-step controller before MPC if necessary.

Require manual kill switch and automated stale-feed/circuit-breaker behavior.

Reconcile orders/fills/account balances after every round.

Compare realized fill price, fee, delay and PnL against predicted values.

Increase limits only after predefined round-count and risk gates.

## Deliverables

Live release checklist.

Round reconciliation report.

Capital ramp policy.

## Verification

Kill-switch drill.

Feed disconnect during open maker order.

Delayed taker order during rapid repricing.

## Exit gate

No unexplained ledger discrepancies.

Tail-loss and drawdown remain within configured limits.

# 17. Phase 14 - Adaptive Optimization and Target-Profile Research

Objective. Use accumulated causal data to improve the controller without turning it into opaque uncontrolled online learning.

## Implementation steps

Estimate state transition matrices and maker fill hazards from the bot's own event log.

Recalibrate probability model on scheduled offline windows.

Optimize G_min, edge_min, maker TTL/churn thresholds and time/volatility weighting by walk-forward objective.

Study public target-wallet behavior only as an economic benchmark (pair buffer, residual exposure, clip/price patterns), not as proof of its private signal logic.

Evaluate contextual bandit/RL approaches only after the deterministic MPC baseline is profitable, stable and fully replayable.

## Deliverables

Calibration pipeline.

Target-profile analytics.

Model promotion policy.

## Verification

Champion/challenger comparison.

Rollback to previous model version.

## Exit gate

No model promoted without out-of-sample and shadow validation.

# 18. Testing Matrix

| Layer | Examples | Cadence |
| --- | --- | --- |
| Unit | Portfolio identities, fee math, tick rounding, feature math, regime mapping | Every commit |
| Property | Random fill sequences, constraint preservation | CI |
| Replay regression | Frozen rounds vs expected decisions | CI / release |
| Causality | Future event injection, timestamp skew | CI / release |
| Execution | Depth, partial fill, maker queue, delay, cancel/replace | Pre-release |
| Resilience | Disconnect, resubscribe, stale feed, book resnapshot | Pre-release |
| Performance | Feed-to-decision latency, optimizer runtime | Every performance build |
| Statistical | Walk-forward, calibration, ablation, bootstrap | Model release |
| Live reconciliation | Orders/fills/fees/balances/settlement | Every live round |

# 19. Observability and UI

The UI must explain why the controller is acting. It must remain read-only with respect to trading logic except for explicitly approved runtime parameters and kill controls.

| Panel | Required fields |
| --- | --- |
| Market | t, tau, P0, TWAP window/value/age, current BTC, G_T, G_S, lead gap, volatility |
| Prediction | q, calibration bucket, regime, key feature contributions |
| Book | UP/DOWN bid/ask, spread, depth, tick size, delay flag |
| Portfolio | U, D, C, Pi_U, Pi_D, G, R, spend |
| Orders | purpose, side, maker/taker, price, qty, TTL, state, queue/fill estimate |
| Controller | candidate actions, EV_after, G_after, reject reason, chosen action |
| Performance | latency, fills, slippage, fees, PnL, drawdown, CVaR |

# 20. Data Schema and Journaling

Minimum records should be normalized enough for analytics but preserve raw messages where legally/operationally appropriate.

| Entity | Fields / purpose |
| --- | --- |
| market_config | condition/token IDs, start/end, tick, min size, fee params, delay flag, TWAP mapping |
| feed_event | source, source_ts, recv_ts, sequence, raw value/hash |
| feature_state | feature_version, decision_ts, all causal features |
| model_output | model_version, q, uncertainty/calibration metadata |
| portfolio_state | U,D,C,Pi_U,Pi_D,G,R |
| candidate_action | action_id, purpose, mode, side, price, qty, EV/G/PnL projections |
| order_event | order_id, submit/cancel/replace/status timestamps |
| fill | order_id, fill price/size/fee, liquidity role |
| settlement | outcome, payout, realized PnL |
| audit | strategy/config/model hashes, skip/reject reasons |

# 21. Risk Gates and Rollback Plan

| Gate | Trigger | Response |
| --- | --- | --- |
| Data gate | TWAP/spot/book stale or clock invalid | No new alpha; cancel vulnerable resting orders; resync. |
| Portfolio gate | G_after < G_min | Reject action regardless of signal. |
| Execution gate | Unexpected tick/fee/delay config | Freeze submissions until runtime config reconciled. |
| Latency gate | Controller misses deadline | Fallback to simpler one-step/WAIT policy. |
| Loss gate | Daily/market drawdown limit | Stop new risk; cancel open orders where safe. |
| Model gate | Calibration/feature drift exceeds threshold | Revert to previous champion or baseline. |
| Ledger gate | Fill/account mismatch | Stop and reconcile before next trade. |

Rollback rule. Every production strategy/model/config promotion must have a one-command rollback to the last known-good version plus a kill switch that blocks new orders.

# 22. Recommended Milestones and Deliverables

| Milestone | Name | Phases | Required output |
| --- | --- | --- | --- |
| M1 | Baseline trustworthy | Phases 0-2 | Reproducible causal replay + event store. |
| M2 | Economic kernel trustworthy | Phase 3 | Exact portfolio simulator and risk constraints. |
| M3 | Signals measurable | Phases 4-5 | Lead-lag feature set + calibrated q model. |
| M4 | Policy encoded | Phase 6 | Seed regime/action matrix. |
| M5 | Execution realistic | Phase 7 | Depth/fee/delay/fill simulation. |
| M6 | Semi-control works | Phases 8-9 | One-step optimizer + proactive order lifecycle. |
| M7 | Timing optimized | Phase 10 | Short-horizon MPC. |
| M8 | Research proof | Phase 11 | Walk-forward + ablation evidence. |
| M9 | Operational proof | Phase 12 | Stable shadow/paper system. |
| M10 | Capital proof | Phase 13 | Limited live results within risk gates. |
| M11 | Continuous improvement | Phase 14 | Scheduled model/calibration promotion pipeline. |

## 22.1 Recommended immediate next sprint

Freeze the baseline and export 200+ representative historical rounds if available.

Implement runtime market metadata, exact TWAP feed mapping, tick size and fee handling.

Build the append-only event store and exact U/D/C portfolio kernel.

Add TWAP gap, current-BTC gap, spot-to-TWAP lead gap, time and volatility features.

Produce the first empirical table: P(UP) and realized edge by gap bucket x spot direction x CLOB direction x time bucket.

Only after that table exists, lock the first seed maker/taker matrix for replay.

# 23. References

| Ref | Source |
| --- | --- |
| [X1] | User-supplied: xamarinbot - Core Trading Strategy & Algorithm (baseline strategy document). |
| [P1] | Polymarket Documentation - Fees, docs.polymarket.com/trading/fees. |
| [P2] | Polymarket Documentation - Orders Overview / Tick Sizes, docs.polymarket.com/trading/orders/overview. |
| [P3] | Polymarket Documentation - Order Lifecycle, docs.polymarket.com/concepts/order-lifecycle. |
| [P4] | Polymarket Documentation - Orderbook, docs.polymarket.com/trading/orderbook. |
| [P5] | Polymarket Documentation - Market WebSocket Channel / tick_size_change, docs.polymarket.com/market-data/websocket/market-channel. |
| [P6] | Polymarket Documentation - Chainlink TWAP Prices, docs.polymarket.com/market-data/chainlink-twap. |